## Sheet1
IMPACT OF EVs ON ENERGY AND CONSUMER BEHAVIOR |  |  | On the 3rd, discuss meeting times going forward
Schedule
| 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10
Project ideation
Elaine | 2023-01-01: Assigned explorations/hypotheses to refine
Deb | bar: 2023-01-01 to 2023-01-02
Ryan | bar: 2023-01-01 to 2023-01-02
Nick | bar: 2023-01-01 to 2023-01-02
Data fetching - gathering data and permissions | 2023-01-02: Fetch databases based on assigned
Elaine | 2023-01-02: Checking Kelley Blue Book
Deb | 2023-01-02: Checking Consumer Reports
Ryan | 2023-01-02: Charging stations,
Nick | bar: 2023-01-02 to 2023-01-03
Data exploration - Understand the structure and characteristics of the collected data | 2023-01-03: Hold - Revisit on Wednesday the 3rd
Elaine | bar: 2023-01-03 to 2023-01-07
Deb | bar: 2023-01-03 to 2023-01-07
Ryan | bar: 2023-01-03 to 2023-01-07
Nick | bar: 2023-01-03 to 2023-01-07
Data transformation - Prepare and clean the data for analysis | 2023-01-03: Hold - Revisit on Wednesday the 3rd
Elaine | bar: 2023-01-03 to 2023-01-07
Deb | bar: 2023-01-03 to 2023-01-07
Ryan | bar: 2023-01-03 to 2023-01-07
Nick | bar: 2023-01-03 to 2023-01-07
Data analysis - Analyze the data to draw meaningful insights | 2023-01-06: Document in READme
Elaine | bar: 2023-01-06 to 2023-01-08
Deb | bar: 2023-01-06 to 2023-01-08
Ryan | bar: 2023-01-06 to 2023-01-08
Nick | bar: 2023-01-06 to 2023-01-08
Testing and Tables - Testing the trends. Validate the results and check for the robustness of the analysis | 2023-01-06: Document in READme
Elaine | bar: 2023-01-06 to 2023-01-08
Deb | bar: 2023-01-06 to 2023-01-08
Ryan | bar: 2023-01-06 to 2023-01-08
Nick | bar: 2023-01-06 to 2023-01-08
Creating documentation - Create READme, document the research process, methods, and results. | 2023-01-08: Everyone submit their READmes to Deb; Deb will compile
Elaine | bar: 2023-01-01 to 2023-01-08
Deb | bar: 2023-01-01 to 2023-01-08
Ryan | bar: 2023-01-01 to 2023-01-08
Nick | bar: 2023-01-01 to 2023-01-08
Creating the presentation | 2023-01-07: Presentation development, revision, and rehearsal
Elaine | 2023-01-10: Present
Deb | bar: 2023-01-07 to 2023-01-10
Ryan | bar: 2023-01-07 to 2023-01-10
Nick | bar: 2023-01-07 to 2023-01-10